## Sheet1
Associated Student Government 2007-2008
Project Tracking Form
Year Long Goals (Goals are not in any particular order)
Enhance pluralism and diversity efforts on campus (1)
Improve Communication and Transparency (2)
Engage more student involvement in college governance (3)
Improve resources available to students (4)
Summer Quarter Projects (Updated 8-8-2007)
# | Name | Description |  | Project Lead | Project Due | Project Status | Goal #
1 | Hire Associate Justice | Recruit, Hire, and Train Associate Justice |  | Jacob | 2007-07-20 | Complete | 3
2 | Hire VPFC | Recruit, Hire, and Train New VP of Finance and Communications |  | Jacob | 2007-08-20 | Incomplete | 3
3 | ASG Training | Organize and Schedule |  | Jacob | End of Sumr | Complete | 2
4 | Communication System | Create ASG Communications Plan |  | Peter | End of Sumr | Incomplete | 2
5 | Financial Tracking | Create and Design Financial Tracking and Reporting System |  | Jacob | 2007-07-18 | Complete | 2
6 | New Space | Complete SP Remodel |  | Jacob | 2007-09-04 | Incomplete | 4
7 | College Committees | Gain Approval for increase students involvement |  | Jacob | 2007-09-04 | Incomplete | 3
8 | Washington State C.T.C. Student Lobby | Create and gain memborship across state |  | Jacob | All Year | Incomplete | 3
9 | Complaint System | Create ASG Complaint System |  | Sergey | 2007-07-24 | Complete | 2
10 | Pluralism Plan | Create ASG Pluralism Plan |  | Sergey | 2007-08-09 | Complete | 1
11 | Student Issues Summit | Create Student Issues Summit |  | Sergey | Fall Quarter | Incomplete | 1
12 | ASG Website | Design and Update ASG Website |  | Justin | 2007-08-20 | Incomplete | 2
13 | College Wide Wireless System | Create College Wide Wireless system |  | Justin | End of Year | Incomplete | 4
14 | Web Forum(MyBCC) | Create ASG Web Forum and Procedure |  | Justin | End of Sumr | Incomplete | 2
15 | Tech Free Agreement Review | Review the tech fee contract with college |  | Justin | End of Year | Incomplete | 4
16 | Tech Fee Amount Adjustment | Adjust tech fee accordingly for optimum student satisfaction |  | Justin | End of Year | Incomplete | 4
17 | Publish Online Documents | Create system for publishing ASG Documents Online |  | Justin | 2007-08-20 | Incomplete | 2
18 | Document and Contact Tracking System | Create, Design, and Implement ASG Document Tracking System |  | Kelsey | 2007-07-20 | Complete | 2
19 | ASG By Law | Create opportunities for Public Input |  | Yoonmi | Fall Quarter | Incomplete | 3
20 | Student Senate | Create, Design, and Implement ASG Student Senate |  | Jorge | End Summer. | Incomplete | 3
21 | Art | Increase Art around Campus |  | ?? | ?? | Incomplete | 4
22 | ASG Judicial Board Official Meeting | Create an ASG Judicial Board Meeting |  | Jorge | 2007-07-13 | Incomplete | 2
23 | ASG Apparel | Design & Order ASG Apparel |  | Peter | End of Fall | Incomplete | 2
24 | Meet-the-ASG Day | Have a Meet and Greet with ASG |  | Peter | End of Fall | Incomplete | 2
25 | Brand Awareness of BCC logo | Create Brand Awareness for BCC Seal |  | Peter | 2007-08-15 | Incomplete | 2
26 | BCC Spirit Week | Create and Organize BCC Sprit Week |  | Peter | End of Fall | Incomplete | 4
27 | Enhance Bus Shelter | Enhance educational material for Bus riders |  | Peter | End of Year | Incomplete | 4
28 | Club summit | Organize Club Summit to discuss issues |  | Marcus | ?? | Incomplete | 2
29 | Green Energy | Gain student approval for Green Energy |  | Lauren | End of Year | Incomplete | 4
30 | Student Financial Center | Create Student Financial Center |  | Lauren | End of Year | Incomplete | 4
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
| Project Totals |  |  | Current | Completed
| Enhance pluralism and diversity efforts on campus (1) |  |  | 2 | 0
| Improve Communication and Transparency (2) |  |  | 12 | 1
| Engage more student involvement in college governance (3) |  |  | 5 | 1
| Improve resources available to students (4) |  |  | 9 | 0
| Name | Current | Completed
| Jacob | 6 | 2
| Sergey | 3 | 0
| New VPFC | 0 | 0
| Lauren | 2 | 0
| Justin | 6 | 0
| Peter | 5 | 0
| Jorge | 2 | 0
| Kelsey | 1 | 0
| Yoonmi | 1 | 0
| Marcus | 1 | 0